## Sheet1
Project Name | TutorialNinja
Client | Masai
Reference Document
Created By | Gite Faneshwar Sunil
Creation Date | 2024-08-29
Approved By | Shiva Kiumar MG
Defect/Bug:
Bug ID | Priority | Description/Bug Summary | Pre-requisities | Bug Steps | Potential Bug | Expected Result | Actual Result | Status | Test Excuted By | Screenshot/Video
BG_AF_001 | High | Homepage links not working | None | 1. Navigate to homepage 2. Click on all links | Link navigation issue | All links should navigate to the correct pages | Some links loading pages | Open | Faneshwar Gite
BG_AF_002 | Medium | Keyword search returns no results | None | 1. Enter keyword in search bar 2. Click search | Search functionality issue | Search should return relevant results | No results are displayed | Open | Faneshwar Gite
BG_AF_003 | High | Affiliate registration form errors | None | 1. Navigate to Affiliate page 2. Fill out form with valid data 3. Email change 4. Submit | Form submission issue | Warning: Number Address is already registered! | Warning: E-Mail Address is already registered! | Open | Faneshwar Gite
BG_AF_004 | Low | Misalignment of product information | None | 1. Navigate to a product page 2. Observe product details | Statistics accuracy issue | Statistics accuracy issue | Statistics data is incorrect | Open | Faneshwar Gite
BG_AF_005 | Medium | Inaccurate affiliate statistics display | Logged in as affiliate | 1. Navigate to Affiliate Dashboard 2. Check statistics | Statistics accuracy issue | Statistics should display correct data | Statistics data is Not Working | Opne | Faneshwar Gite
BG_AF_006 | High | Affiliate link tracking fails | Logged in as affiliate | 1. Generate affiliate link 2. Click on the link and make a purchase | Tracking issue | Clicks should be tracked and attributed to the affiliate | Not option Displayed | Opne | Faneshwar Gite
BG_AF_007 | Medium | Incorrect commission calculation | Logged in as affiliate | 1. Complete a purchase via affiliate link 2. Check commission report | Calculation error | Commission should match the defined percentage of the sale | Commission amount is incorrect | Opne | Faneshwar Gite
BG_AF_008 | High | Affiliate dashboard not loading | Logged in as affiliate | 1. Navigate to Affiliate Dashboard | Dashboard loading issue | Dashboard should load and display relevant information | Desktops category is not respoding | Opne | Faneshwar Gite
BG_AF_009 | Medium | Affiliate account approval email not received | None | 1. Register as an affiliate 2. Check email for approval | Email Issue | An approval email should be received within a reasonable time | No email received not showing displayed | Opne | Faneshwar Gite
BG_AF_010 | Low | Missing affiliate terms and conditions link | None | 1. Navigate to Affiliate page | Terms and conditions missing | Terms and conditions should be clearly visible and accessible | No link or information provided | Opne | Faneshwar Gite
BG_AF_011 | Medium | Affiliate referral code not generating | Logged in as affiliate | 1. Navigate to Affiliate Dashboard 2. Attempt to generate referral code | Referral code generation issue | Referral code should be generated and displayed | Referral code not generated | Opne | Faneshwar Gite
BG_AF_012 | High | Duplicate affiliate registrations allowed | None | 1. Register multiple times with the same email address | Registration issue | Duplicate registrations should be prevented | accounts created with the same email address | Opne | Faneshwar Gite
BG_AF_013 | Medium | Inconsistent currency display in affiliate earnings | Logged in as affiliate | 1. Navigate to Affiliate Dashboard 2. Check earnings in different currencies | Currency display issue | Earnings should be displayed consistently in the chosen currency | Currency format or amount is inconsistent | Opne | Faneshwar Gite
BG_AF_014 | High | Broken link to affiliate promotional materials | Logged in as affiliate | 1. Navigate to Affiliate Dashboard 2. Click on promotional materials link | Link issue | Link should direct to the correct promotional materials | Link loading page 3.5 second | Opne | Faneshwar Gite
BG_AF_015 | Low | Non-functional "Contact Support" button on Affiliate page | None | 1. Navigate to Affiliate page 2. Click "Contact Support" button | Button functionality issue | Button should open a contact support form or email client | Button does nothing when clicked | Opne | Faneshwar Gite
BG_AF_016 | Medium | Incorrect display of affiliate banners | Logged in as affiliate | 1. Navigate to Affiliate Dashboard 2. Check the displayed banners | Banner display issue | Banners should be displayed correctly and as per the design | Banners are misaligned or not displaying properly | Opne | Faneshwar Gite
BG_AF_017 | High | Affiliate account not updating correctly | Logged in as affiliate | 1. Make changes to account details 2. Save changes and reload the page | Account update issue | Changes should be saved and displayed correctly | Changes are Wrong information saved or displayed | Opne | Faneshwar Gite
BG_AF_018 | Medium | Affiliate link redirects to incorrect page | Logged in as affiliate | 1. Generate affiliate link 2. Click the link and check redirection | Redirection issue | Affiliate link should redirect to the correct product or landing page | Redirects to a different or incorrect page | Opne | Faneshwar Gite
BG_AF_019 | Low | Inconsistent formatting of affiliate email notifications | Logged in as affiliate | 1. Trigger an email notification 2. Check email formatting | Email formatting issue | Email notifications should be consistently formatted | Email formatting is inconsistent | Opne | Faneshwar Gite
BG_AF_020 | High | Affiliate earnings report not downloadable | Logged in as affiliate | 1. Navigate to Affiliate Dashboard 2. Attempt to download the earnings report | Report download issue | Earnings report should be downloadable in a standard format (e.g., CSV) | Report download fails or does not start | Opne | Faneshwar Gite
BG_AF_021 | Medium | Incorrect total earnings displayed on dashboard | Logged in as affiliate | 1. Navigate to Affiliate Dashboard 2. Check total earnings | Earnings calculation issue | Total earnings should match the sum of individual earnings | Total earnings are incorrect | Opne | Faneshwar Gite